## Plan Summary
Activiti Engineering Resource Plan (September 2004 to January 2005)
Prepared by Nigel Dore 27/09/2004
Projects, Phases and Effort Availability (Calculated) | [5 empty] | Activity by 1/2 Week (Calculated)
Project | RUP Phase | Timebox |  | Man-days |  |  | 2004-09-27 |  | 2004-10-04 |  | 2004-10-11 |  | 2004-10-18 |  | 2004-10-25 |  | 2004-11-01 |  | 2004-11-08 |  | 2004-11-15 |  | 2004-11-22 |  | 2004-11-29 |  | 2004-12-06 |  | 2004-12-13 |  | 2004-12-20 |  | 2004-12-27 |  | 2004-01-03 |  | 2004-01-10 |  | 2004-01-17 |  | 2004-01-24 |  | 2004-01-31 |  | 2004-02-07
|  |  |  | Available |  |  |  | 2004-09-29 |  | 2004-10-06 |  | 2004-10-14 |  | 2004-10-21 |  | 2004-10-27 |  | 2004-11-03 |  | 2004-11-10 |  | 2004-11-17 |  | 2004-11-24 |  | 2004-12-01 |  | 2004-12-08 |  | 2004-12-15 |  | 2004-12-22 |  | 2004-12-29 |  | 2004-01-05 |  | 2004-01-12 |  | 2004-01-19 |  | 2004-01-26 |  | 2004-02-02 |  | 2004-02-09
Miscellaneous | Other | O |  | 116 |  |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 0 | 3 | 2 | 2 | 3 | 4 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2
| Holiday | H |  | 68 |  |  | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 13 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unused |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Unused |  |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V2.0 (V2) | Inception | V2I |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Elaboration | V2E |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction | V2C1 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction | V2C2 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction | V2C3 |  | 82 |  |  | 10 | 12 | 9 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Transition | V2T |  | 126 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 7 | 11 | 8 | 9 | 7 | 7 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quality (Q) | Construction | Q2 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction | Q3 |  | 50 |  |  | 0 | 0 | 0 | 0 | 13 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction | Q4 |  | 66 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 5 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction | Q5 |  | 40 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V2.1 | Inception | V3I |  | 14 |  |  | 2 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Elaboration | V3E |  | 98 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 2 | 5 | 3 | 6 | 6 | 7 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction | V3C1 |  | 196 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 9 | 8 | 9 | 9 | 8 | 9 | 9 | 0 | 5 | 7 | 7 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Transition | V3T |  | 70 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 6 | 5 | 4 | 7 | 4
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
V2.5 | Inception | V4I |  | 34 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Elaboration | V4E |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 5 | 5 | 6 | 6 | 4 | 7
Total (man-days) |  |  |  | 960
Allocation to Timeboxes/Projects (Input)
HolsToBk
|  |  | Kevin |  | 8 |  | V2C3 | V2C3 | V2C3 | V2C3 | Q3 | Q3 | V2T | V2T | V2T | V2T | V2T | V2T | V2T | V2T | Q4 | Q4 | Q4 | Q4 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | H | V3C1 | V3C1 | V3C1 | V3C1 | Q5 | Q5 | V4E | V4E | V4E | V4E | V4E | V4E | V4E
|  |  | Richard |  | 10 |  | V2C3 | V2C3 | V2C3 | V2C3 | Q3 | Q3 | V2T | V2T | V2T | V2T | V2T | V2T | V2T | V2T | Q4 | Q4 | O | O | O | O | O | O | O | O | O | O | H | O | O | O | O | O | O | O | O | O | O | O | O | O
|  |  | Roy |  | 0 |  | V2C3 | V2C3 | V2C3 | V2C3 | Q3 | Q3 | V2T | V2T | V2T | V2T | H | V3E | V3E | V3E | V3E | V3E | H | H | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | H | H | H | H | V3C1 | Q5 | Q5 | V3T | V3T | V3T | V3T | V3T | V3T | V3T
|  |  | Andy |  | 8 |  | V2C3 | V2C3 | V2C3 | V2C3 | Q3 | Q3 | V2T | V2T | V2T | V2T | V2T | V2T | V2T | V2T | Q4 | Q4 | Q4 | Q4 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | H | V3C1 | V3C1 | V3C1 | V3C1 | Q5 | Q5 | V4E | V4E | V4E | V4E | V4E | V4E | V4E
|  |  | Derek |  | 15 |  | V2C3 | V2C3 | V2C3 | V2C3 | Q3 | H | H | H | V2T | V2T | V2T | V3E | V3E | V3E | V3E | V3E | Q4 | Q4 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | H | V3C1 | V3C1 | V3C1 | V3C1 | Q5 | Q5 | V3T | V3T | V3T | V3T | V3T | V3T | V3T
|  |  | Gavin |  | 0 |  | V2C3 | V2C3 | H | H | Q3 | Q3 | V2T | V2T | V3E | V3E | V3E | V3E | V3E | V3E | V3E | V3E | Q4 | Q4 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | H | H | H | H | V3C1 | Q5 | Q5 | V3T | V3T | V3T | V3T | V3T | V3T | V3T
|  |  | Nigel M |  | 9 |  | V2C3 | V2C3 | V2C3 | V2C3 | Q3 | Q3 | V2T | V2T | V2T | V2T | V2T | V2T | V2T | V2T | Q4 | Q4 | O | O | O | O | O | O | O | O | O | O | H | O | O | O | O | O | O | O | O | O | O | O | O | O
|  |  | Jan |  | 4 |  | V2C3 | V2C3 | V2C3 | V2C3 | Q3 | Q3 | V2T | V2T | V2T | V2T | V2T | V2T | V2T | V2T | Q4 | Q4 | Q4 | Q4 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | H | V3C1 | V3C1 | V3C1 | V3C1 | Q5 | Q5 | V4E | V4E | V4E | V4E | V4E | V4E | V4E
|  |  | Dave |  | 11 |  | V2C3 | V2C3 | V3I | V2C3 | Q3 | Q3 | V2T | V3E | V2T | V3E | V2T | V3E | V2T | V3E | Q4 | V3E | Q4 | Q4 | V3C1 | V4I | V3C1 | V3C1 | V4I | V3C1 | V3C1 | V4I | H | V3C1 | V4I | V3C1 | V3C1 | Q5 | Q5 | V4E | V3T | V4E | V3T | V4E | V3T | V4E
|  |  | Linton |  | 0 |  | V2C3 | V2C3 | V2C3 | V3I | Q3 | Q3 | V3E | V3E | V2T | V3E | V2T | V3E | V3E | V3E | V3E | V3E | Q4 | Q4 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | V3C1 | H | V4I | V3C1 | V4I | V4I | Q5 | Q5 | V4E | V4E | V3T | V4E | V4E | V3T | V4E
|  |  | Tim |  | 11 |  | O | V3I | O | V3I | Q3 | Q3 | V3E | O | V3E | V2T | V3E | V2T | V3E | O | V3E | V3E | Q4 | Q4 | V4I | V3C1 | O | V4I | V3C1 | O | V4I | V3C1 | H | O | V4I | V3C1 | O | O | Q5 | V4E | O | V3T | V4E | O | V3T | V4E
|  |  | Anne |  | 0 |  | V3I | V2C3 | V2C3 | V2C3 | Q3 | Q3 | V2T | V3E | V2T | V3E | V2T | V3E | V2T | V3E | Q4 | V3E | Q4 | Q4 | V3C1 | V4I | H | H | H | H | H | H | H | H | V3C1 | V4I | V3C1 | Q5 | Q5 | V4E | V3T | V4E | V3T | V4E | V3T | V4E
|  |  | Paul |  | 5 |  | V3I | V2C3 | V3I | V2C3 | Q3 | Q3 | V3E | V3E | V2T | V3E | V3E | V2T | V3E | V3E | Q4 | V3E | Q4 | Q4 | V3C1 | V3C1 | V4I | V3C1 | V3C1 | V4I | V3C1 | V3C1 | H | V4I | V3C1 | V3C1 | V4I | O | Q5 | V3T | V4E | V3T | V4E | V3T | V4E | V3T
|  |  | Total |  | 81 |  | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
Totals by Project Phase (Calculated)
|  |  |  | Man-days |  |  | D2I | D2E | D2C | V3T | V3I | V3E | V4I | V4E | V2C3 | V2T | O | Q3 | Q4 | Q5 | V3C1 | H | [5 empty] | Ratios in shared time boxes (marked yellow)
|  |  | Kevin | 80 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 8 | 16 | 0 | 4 | 8 | 4 | 24 | 2 | [7 empty] | V2C3 | V3I | O |  | V2T | V3E | O |  | V3C1 | V4I | O |  | V3T | V4E | 0
|  |  | Richard | 80 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 | 46 | 4 | 4 | 0 | 0 | 2
|  |  | Roy | 80 |  |  | 0 | 0 | 0 | 14 | 0 | 10 | 0 | 0 | 8 | 8 | 0 | 4 | 0 | 4 | 18 | 14 | [5 empty] | Dave |  | 70 | 30 | 0 |  | 50 | 50 | 0 |  | 70 | 30 | 0 |  | 50 | 50 | 0
|  |  | Andy | 80 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 8 | 16 | 0 | 4 | 8 | 4 | 24 | 2 | [5 empty] | Linton |  | 70 | 30 | 0 |  | 20 | 80 | 0 |  | 75 | 25 | 0 |  | 20 | 80 | 0
|  |  | Derek | 80 |  |  | 0 | 0 | 0 | 14 | 0 | 10 | 0 | 0 | 8 | 6 | 0 | 2 | 4 | 4 | 24 | 8 | [5 empty] | Tim |  | 25 | 50 | 25 |  | 25 | 50 | 25 |  | 33 | 33 | 33 |  | 33 | 33 | 33
|  |  | Gavin | 80 |  |  | 0 | 0 | 0 | 14 | 0 | 16 | 0 | 0 | 4 | 4 | 0 | 4 | 4 | 4 | 18 | 12 | [5 empty] | Anne |  | 75 | 25 | 0 |  | 50 | 50 | 0 |  | 60 | 40 | 0 |  | 50 | 50 | 0
|  |  | Nigel | 80 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 16 | 46 | 4 | 4 | 0 | 0 | 2 | [5 empty] | Paul |  | 50 | 50 | 0 |  | 30 | 70 | 0 |  | 70 | 30 | 0 |  | 50 | 50 | 0
|  |  | Jan | 80 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 8 | 16 | 0 | 4 | 8 | 4 | 24 | 2
|  |  | Dave | 80 |  |  | 0 | 0 | 0 | 6 | 2 | 10 | 8 | 8 | 6 | 8 | 0 | 4 | 6 | 4 | 16 | 2
|  |  | Linton | 80 |  |  | 0 | 0 | 0 | 4 | 2 | 16 | 6 | 10 | 6 | 4 | 0 | 4 | 4 | 4 | 18 | 2
|  |  | Tim | 80 |  |  | 0 | 0 | 0 | 4 | 4 | 12 | 8 | 6 | 0 | 4 | 22 | 4 | 4 | 2 | 8 | 2
|  |  | Anne | 80 |  |  | 0 | 0 | 0 | 6 | 2 | 10 | 4 | 8 | 6 | 8 | 0 | 4 | 6 | 4 | 6 | 16
|  |  | Paul | 80 |  |  | 0 | 0 | 0 | 8 | 4 | 14 | 8 | 6 | 4 | 4 | 2 | 4 | 6 | 2 | 16 | 2
Parameters (Input ) | [6 empty] | Future Dates (2005) |  |  |  |  | Approx developer effort
Unknown Holiday/Sick Adj |  | 0.05 |  |  |  |  | V3C1 end |  | Jan 12th |  |  | V3E | 36 | man-days |  |  | V2T | 98 | man-days
Contingency / Support |  | 0.15 |  |  |  |  | V3T end |  | Feb 16th |  |  | V3C1 | 104 | man-days |  |  | V3T | 42 | man-days
Availability |  | 0.8 | [9 empty] | V4E | 63 | man-days

## V2C3Analysis
Fix in Timebox | V2C3
Sum of To Do | Timebox Priority
Assigned To | 1 - Must | 2 - Should | 3 - Could | Grand Total | M+S | Availability | Diff | Worked | LastPlan | WorkDone | adj | RealWork | Eff
Andy Hind | 9 | 0 | 15.4 | 24.4 | 9 | 8 | -1 | 5 | 11.5 | 2.5 | 0 | 2.5 | 50
Anne Whitty | 8 |  |  | 8 | [7 empty] | 0
David Caruana | 6.7 | 0 | 1 | 7.7 | 6.7 | 6 | -0.7 | 2.5 | 10 | 3.3 | -0.5 | 2.8 | 112
Derek Hulley | 8.25 | 0 |  | 8.25 | 8.25 | 8 | -0.25 | 5 | 12 | 3.75 | 0 | 3.75 | 75
Gav Cornwell | 5.75 |  |  | 5.75 | 5.75 | 4 | -1.75 | 5 | 8.75 | 3 | 0 | 3 | 60
Jan Vonka | 7.5 |  |  | 7.5 | 7.5 | 8 | 0.5 | 5 | 9 | 1.5 | 0.5 | 2 | 40
Kevin Roast | 7.5 | 2 | 0.5 | 10 | 9.5 | 8 | -1.5 | 5 | 13.5 | 4 | 0 | 4 | 80
Nigel Magnay | 6.5 |  |  | 6.5 | 6.5 | 8 | 1.5 | 1 | 9.25 | 2.75 | 0 | 2.75 | 275
Paul Holmes-Higgin | 0 | 2 |  | 2 | [7 empty] | 0
Richard Hodges | 9.45 | 1 |  | 10.45 | 10.45 | 8 | -2.45 | 5 | 13.3 | 2.85 | 0 | 2.85 | 57
Roy Wetherall | 5.6 | 3.01 | 7.3 | 15.91 | 8.61 | 8 | -0.61 | 5 | 12.5 | 3.89 | 0 | 3.89 | 77.8
Grand Total | 74.25 | 8.01 | 24.2 | 106.46
[5 empty] | 72.26 | 66 | -6.26 | 38.5 | 99.8 | 27.54
Efficiency v Plan | 71.5325

## PTTasks
PRN | Title | Assigned To | Fix in Timebox | Timebox Priority | Required in Release | Status | Estimated Size | Remaining Effort | Actual Size | To Do | PrevToDo | WorkDone
3765 | port company wide joiners leavers macros (1) | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 0.3 | 0.3 | 0 | 0.3 | 0.3 | 0
2754 | Office start date not being used in Pivot table as at date | Andy Hind | Q3 | 1 - Must | 2 | In Development | 2 | 0 | 0 | 2 | 2 | 0
3804 | Add id and provide to amcro definitions as loaded if missing | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 0.2 | 0.2 | 0 | 0.2 | 0.2 | 0
3799 | Initialise macros and answers | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.2 | 0 | 0.2 | 0.2 | 0
3794 | Expand by hierarchy for join - up and down | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.1 | 2 | 0.1 | 0.5 | 0.4
3791 | Hierarchy for joins via role in cube implementation | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3788 | date population on the data base rather than MBean | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3785 | Indicate total to use for percentage calculations | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 0.2 | 0.2 | 0 | 0.2 | 0.2 | 0
3782 | Add formatting control to data column and roll ups | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3779 | Specify the name of the total roll up in groupings | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 0.2 | 0.2 | 0 | 0.2 | 0.2 | 0
3772 | Add support to filter using like in attributes | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3770 | Provide estimates of macro execution times to the user | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 2 | 2 | 0 | 2 | 2 | 0
3769 | Generate textual descriptions of macros | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 1 | 0.8 | 0 | 0.8 | 1 | 0.2
3805 | Regression test remainaing macros | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 1.5 | 1.3 | 0 | 1.3 | 1.5 | 0.2
3767 | Macros - support adding missing enums to roll ups (blanks) | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 2 | 2 | 0 | 2 | 2 | 0
3807 | Ordering functions for grouping | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3764 | Port the investment professionals macros (9) | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 1 | 0.5 | 0 | 0.5 | 1 | 0.5
3763 | Macro ports for N/L (9) | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 1.5 | 1.5 | 0 | 1.5 | 1.5 | 0
3762 | Get Used attributes for macro and cube -> event support | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3761 | Macro Events - predicate use | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 2 | 2 | 0 | 2 | 2 | 0
3758 | Cube definition for company wide joiners and leavers | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3757 | Functions for new lost cube | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3756 | Add cube definitions for new/lost | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3755 | Function definitions for the joiners leavers cube | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3754 | Definitions for the Joiners/Leavers cube | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3753 | Unit tests for the macro framework | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 2 | 2 | 0 | 2 | 2 | 0
3752 | Performance tests for the macro framework | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3363 | Account with AUM closing value only showed up in the AUM wizard list | Andy Hind | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3768 | Indexes for macro performance | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 2 | 2 | 0 | 2 | 2 | 0
2687 | Wizards - as they are slow would like to be able to cancel | Andy Hind | V2C3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3504 | OLAP- Cube definition for personnel | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 1 | 0.1 | 0 | 0.1 | 0.3 | 0.2
3514 | Count of Joiners Leavers does unique count for individual | Andy Hind | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
2751 | Wizard Joiners and Leavers as at 2003 date when IP start today | Andy Hind | Q3 | 1 - Must | 2 | In Development | 1 | 0 | 0 | 1 | 1 | 0
3822 | Update existing BAT documents for V2.0 | Anne Whitty | V2C3 | 1 - Must | 2 | In Development | 5 | 5 | 0 | 5 | 5 | 0
3821 | Create BAT tests for new V2 functionality | Anne Whitty | V2C3 | 1 - Must | 2 | In Development | 3 | 3 | 0 | 3 | 3 | 0
3375 | Account on QA filprod causes infinite loop on save | David Caruana | Q3 | 1 - Must | 1.2.2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5 | 0
3380 | Import and Validation reports display redundant navigation arrows | David Caruana | V2C3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3299 | Cannot set an end date for office with no employees | David Caruana | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3381 | Typo - Use of adverb 'maybe' should be replaced by 'may be' | David Caruana | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
1794 | Register and eventing should interact on entity deletions | David Caruana | Q3 | 3 - Could | 1.2.2 | In Development | 2 | 0 | 0 | 2 | 2 | 0
3731 | Conformance: Appl. Integration: Port Rules (Office, AUM) | David Caruana | V2C3 | 1 - Must | 2 | In Development | 2 | 0.1 | 0 | 0.1 | 2 | 1.9
3734 | Conformance: Engine: Rule Locking | David Caruana | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.1 | 0 | 0.1 | 0.5 | 0.4
3777 | Missing staging area cm index on associations and roles | David Caruana | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
1226 | No way of defining indexes for attribute on associations | David Caruana | TBD | 3 - Could | TBD | In Development | 0 | 0 | 0 | 0 | 0 | 0
3697 | Appropriate content translator should be used in HTTP Query Service | David Caruana | Q3 | 1 - Must | 2 | In Development | 0.5 | 0 | 0 | 0.5 | #N/A | #N/A
3856 | Adding documents to a loaded opportunity gives error(409) conflict | David Caruana | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3698 | Workarea service should be doing business logic checks | David Caruana | V2C3 | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 2 | 0
3848 | Specifically reference an assoc in an MQL statement and not return it crashes | David Caruana | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3738 | Conformance: Appl. Integration: Port Rules (Remaining) | David Caruana | V2C3 | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 2 | 0
2852 | Some changes to product features allowed for 'locked' entity. | David Caruana | TBD | 1 - Must | TBD | In Development | 0 | 0 | 0 | 0 | 0 | 0
941 | DDClass getOperations() - wrong for soft type | David Caruana | Q3 | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
147 | Cannot specify type or attribute names that are reserved database words | David Caruana | TBD | 3 - Could | TBD | In Development | 0 | 0 | 0 | 0 | 0 | 0
146 | Cannot create entities with no attributes | David Caruana | Q3 | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3739 | Conformance: Appl. Integration: Port Validation Macros to Rules | David Caruana | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3886 | Trigger error for circular (or duplicate) links - subsidiary companies / teams | David Caruana | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
2543 | Cannot specify domicile for employee in the UI | David Caruana | TBD | 1 - Must | TBD | In Development | 0 | 0 | 0 | 0 | 0 | 0
3625 | Inserts or updates of data into the hub cause the client to hang | David Caruana | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3465 | Fix Integrity issues fails - unable to find HubSupportService | David Caruana | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
1324 | IDs not treated uniquely between staging areas | David Caruana | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3629 | Bridge table type needs all relationships | David Caruana | Q3 | 1 - Must | TBD | In Development | 0 | 0 | 0 | 0 | 0 | 0
3434 | Attributed Aggregated associations not visible in DDClass | David Caruana | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
1371 | XResultSet API needs refactoring | David Caruana | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3827 | Edit product creates two new versions on each edit | David Caruana | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3693 | Database Profile of Create Workarea, Import Data, Remove Workarea & Repeat | David Caruana | Q2 | 1 - Must | 2 | In Development | 1 | 0 | 0 | 1 | 1 | 0
3813 | Draft content workarea at bootstrap | David Caruana | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3278 | Events: Cleanup ChangeStack and remove old events framework | David Caruana | V2C3 | 3 - Could | 2 | In Development | 2 | 1 | 0 | 1 | 2 | 1
3854 | MQL bug - Order by xyz DESC not working | David Caruana | Q3 | 1 - Must | TBD | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3815 | Publish single entity in workarea | David Caruana | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3627 | AUM validation macos - do not use account identifier functions | David Caruana | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3520 | dbValidate Null pointer on build 282 | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3521 | dbValidate errors with association class | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3522 | Validate and Publish gave failure and 404 and 500 errors displaying the report | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
2907 | Import of specific CDB macro fails due to case sensitive title | Derek Hulley | Q3 | 2 - Should | 2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5 | 0
2531 | Focus of CDB grid is not maintained after edits, etc. | Derek Hulley | TBD | 3 - Could | 1.2.2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5 | 0
2661 | CDB Template New Question set dialog should not close after adding question set | Derek Hulley | TBD | 3 - Could | 1.2.2 | In Development | 1.5 | 0 | 0 | 1.5 | 1.5 | 0
3737 | Conformance: Appl. Integration: Workarea Integration | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 3 | 0 | 0 | 3 | 3 | 0
2257 | Copying questions would a useful feature. | Derek Hulley | TBD | 3 - Could | 1.2.2 | In Development | 1 | 0 | 0 | 1 | 1 | 0
2337 | CDB Template does not display a column for question set type | Derek Hulley | Q3 | 2 - Should | 2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5 | 0
2255 | Cannot associate a consultant company to a CDB. | Derek Hulley | TBD | 1 - Must | TBD | In Development | 1 | 0 | 0 | 1 | 1 | 0
3470 | Integrity errors in AUM import validation | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3386 | Concurrent use - Mapper for import can be changed in UI after import | Derek Hulley | Q3 | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3467 | Validation report Integrity issues are shown with an intity ID GUID | Derek Hulley | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3396 | Full Text Search of information in table fails to match | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3005 | Can add AUM values to Closed accounts after the end date | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5 | 0
3456 | Content webservices/manager etc - stress and performance testing | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 2 | 0 | 0 | 2 | 2 | 0
3462 | Loss of database connection after validating workarea | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3656 | Validation fails for Fidelity Q2 data | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3468 | Fix Integrity issues should only be available to admin user | Derek Hulley | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3419 | Adding a product in a workarea produces validation error | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3705 | Model Cleanup - Remove unused components | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 1.5 | 1.5 | 0 | 1.5 | 1.5 | 0
3471 | Integrity errors in Employee import validation | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
1490 | Can't copy/clone a question set | Derek Hulley | TBD | 3 - Could | 1.2.2 | In Development | 1 | 0 | 0 | 1 | 1 | 0
2480 | Employee mapper should be updated - include email address | Derek Hulley | TBD | 3 - Could | 1.2.2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5 | 0
3735 | Conformance: Engine: Staging Area based events and execution context | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 1 | 0.5 | 0 | 0.5 | 1 | 0.5
3661 | Itemfield unit tests to be based on checking of intermediate xml | Derek Hulley | Q2 | 1 - Must | 2 | In Development | 2 | 0.5 | 0 | 0.5 | 0.5 | 0
2518 | Translator mechanism in mappers issue | Derek Hulley | TBD | 3 - Could | 1.2.2 | In Development | 3 | 0 | 0 | 3 | 3 | 0
2994 | Export answers threw error with a word document in sharepoint open | Derek Hulley | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3196 | No CDB concurrancy use warning when answer status is being updated | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3243 | Deletion of entities does not check the staging area | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3816 | Content history method | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.25 | 0 | 0.25 | 0.5 | 0.25
3362 | Typo in the error output from db-vallidate | Derek Hulley | Q3 | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3238 | Import mapper errors against incorrect import file type. | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3801 | Validation error | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3213 | Investment Target Mapper only works with equity products | Derek Hulley | V2C3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3202 | Error hidden on Export Answers fail with missing currency conversion | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3201 | CDB Question Set - change Question Set type warning is incorrect | Derek Hulley | Q3 | 2 - Should | TBD | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3817 | View content version method | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.25 | 0 | 0.25 | 0.5 | 0.25
3199 | CDB concurrent use error - delete product during export answers | Derek Hulley | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
1768 | Icons in the grid for workareas do not change to reflect there status. | Derek Hulley | Q3 | 2 - Should | 2 | In Development | 0.25 | 0 | 0 | 0.25 | 0.25 | 0
3863 | Write MQL for Canned Queries | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 0.75 | 0.75 | 0 | 0.75 | 0.75 | 0
3078 | CDB mark all as updated warning dialog is same for outdated | Derek Hulley | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3343 | Answer Selector Test UI | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 0.25 | 0.25 | 0 | 0.25 | 0.25 | 0
3759 | Eventing suport for macros at the entity/attribute layer | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 2 | 1 | 0 | 1 | 1 | 0
3351 | Migration Analysis Macros | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3350 | Migration Analysis CDB | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3349 | CDB Test UI | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 1 | 0.5 | 0 | 0.5 | 0.5 | 0
3348 | CDB UI Code Fixes | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 2 | 0.25 | 0 | 0.25 | 0.5 | 0.25
3145 | Vehicle Identifiers do not have to be unique within datasource | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3630 | Item field pre-parser rounding <data> tag entry | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 1 | 0 | 0 | 1 | 1 | 0
3352 | Migration Analysis Core Content | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3824 | Transaction not allowed error during IntegrationService System Test | Gav Cornwell | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3637 | Plugin: Answer tasks to appear on the answer doc info panel | Gav Cornwell | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3636 | Plugin: Asnwer details on the doc info panel | Gav Cornwell | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3875 | Fund - Updating Status to Draft did not show in Fund list | Gav Cornwell | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3138 | Bootstrap lossreasonenum contains ID with FIDELITY in it | Gav Cornwell | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3426 | Errors traced out to hub console should be better handled | Gav Cornwell | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3425 | Error shown on login with no username or password | Gav Cornwell | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3137 | After timeout in the admin console I can not launch the JMX console | Gav Cornwell | Q3 | 3 - Could | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3444 | Edit fails for csv file in workarea - changes are not saved. | Gav Cornwell | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3855 | WIth loaded Test Data for Opportunities - error on selecting row in grid | Gav Cornwell | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3458 | Examine error gives 404 trying to access /diagnostics/error/index.jsp | Gav Cornwell | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3443 | Edit File opening with internet explorer | Gav Cornwell | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3613 | Adding file of the same name can be uploaded onto the WebDav server, causes an e | Gav Cornwell | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3708 | CDB - Hook up the answer selector | Gav Cornwell | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3869 | Refresh button on Show: My Teams does not refresh after adding team | Gav Cornwell | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3710 | CDB - Answer Preview Integration | Gav Cornwell | V2C3 | 1 - Must | 2 | In Development | 0.25 | 0.25 | 0 | 0.25 | 0.25 | 0
3696 | Public AuthenticationService does not have logout method | Gav Cornwell | Q3 | 1 - Must | 2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5 | 0
3866 | UserSelector performance is very poor after latest changes | Gav Cornwell | Q3 | 1 - Must | 2 | In Development | 0.25 | 0.25 | 0 | 0.25 | #N/A | #N/A
3870 | New Team DynaCrud OK button is enabled and focus not set | Gav Cornwell | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3066 | Employee validation required to ensure name is equivalent to forename surname | Gav Cornwell | Q3 | 2 - Should | 2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5 | 0
3871 | Timeout on New Team Dialog gave index error | Gav Cornwell | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3877 | Clients - Updating Status to Draft did not show in Clients list | Gav Cornwell | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3876 | Fund - Status should have non-draft value, not just Draft and Undefined | Gav Cornwell | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3709 | CDB - Implement rendering | Gav Cornwell | V2C3 | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 2 | 0
3300 | Error with use of 'enter' in Create New User | Gav Cornwell | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3711 | CDB - Final integration test (does it all work) | Gav Cornwell | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3217 | concurrent Use warning persists after the user has finished using the record. | Gavin Fothergill | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3212 | JMX pages in admin console need to be made generic | Jan Vonka | Q3 | 2 - Should | 2 | In Development | 2 | 0 | 0 | 2 | 2 | 0
3668 | Integrate new test data into head and continuous build | Jan Vonka | V2C3 | 1 - Must | 2 | In Development | 4 | 1.5 | 0 | 1.5 | 2 | 0.5
3729 | Conformance: Register: Register Transaction Class | Jan Vonka | V2C3 | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 2 | 0
3296 | Websphere Port: Port Configuration Services | Jan Vonka | V2T | 3 - Could | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3295 | Websphere Port: Port JMS Usage | Jan Vonka | V2T | 1 - Must | 2 | In Development | 1 | 0.5 | 0 | 0.5 | 0.5 | 0
3677 | AIX Port: Installer / Uninstaller | Jan Vonka | V2T | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 2 | 0
3294 | Websphere Port: JBoss 3.2 Compatibility | Jan Vonka | V2T | 3 - Could | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3675 | AIX Port: Setup Server Environment for WAS | Jan Vonka | V2T | 1 - Must | 2 | In Development | 2 | 0.5 | 0 | 0.5 | 0.5 | 0
3676 | AIX Port: Regression Test | Jan Vonka | V2T | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 2 | 0
3292 | Websphere Port: Regression Test | Jan Vonka | V2T | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 2 | 0
3293 | Websphere Port: Installer / Uninstaller | Jan Vonka | V2T | 1 - Must | 2 | In Development | 2 | 4 | 0 | 4 | 4 | 0
3291 | Websphere Port: Continuous Build Process | Jan Vonka | V2C3 | 1 - Must | 2 | In Development | 3 | 0.5 | 0 | 0.5 | 2 | 1.5
3730 | Conformance: Appl. Integration: DynaCRUD Integration | Jan Vonka | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3290 | Websphere Port: Port JMX Usage | Jan Vonka | V2T | 2 - Should | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3289 | Websphere Port: Fix Compliance Issues | Jan Vonka | V2T | 1 - Must | 2 | In Development | 3 | 0.5 | 0 | 0.5 | 0.5 | 0
3736 | Conformance: Engine: Hub based execution context | Jan Vonka | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3288 | Websphere Port: Port Web Services | Jan Vonka | Q2 | 1 - Must | 2 | In Development | 3 | 0.5 | 0 | 0.5 | 0.5 | 0
3740 | Conformance: Admin: Hub Conformance Utility | Jan Vonka | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3725 | Conformance: Engine: Transaction based events and execution context | Jan Vonka | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3205 | Case for failure of concurrent modification warning | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3220 | New Mindmap locations after use are not properly deleted | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3221 | Adding new Office for internal company adds a blank line | Kevin Roast | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3373 | Empty dialogs generated from account after timeout. | Kevin Roast | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3325 | UI Parameters Wizard - UI Implementation Code | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 2 | 0.5 | 0 | 0.5 | 0.5 | 0
3366 | Ordering of the mindmap catergories and macros differ published cf staging | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3379 | Company Entity for account allows duplicates and no roles for company | Kevin Roast | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3553 | Document preview view | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 1 | 0.5 | 0 | 0.5 | 0.5 | 0
3023 | Deleting value form the LOV editor - in use notification does not detail object | Kevin Roast | Q3 | 2 - Should | 2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5 | 0
3225 | Adding Office cannot determine external or internal office | Kevin Roast | Q3 | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3421 | Edit vehicle with two spaces threw error in confusion with 1 space version | Kevin Roast | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3357 | Fund Manager Query for vehicle is returning IPs without relation to product | Kevin Roast | TBD | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3427 | Concurrent edit of account numbers missing warnings | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3001 | To-Do lists are avaiable in Admin role, should be suppressed | Kevin Roast | TBD | 3 - Could | 1.2.2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3401 | Double Click enabled for Dynacrud Selection Lists | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3318 | Account Details Copy view to clipboard only copies Company Entity Details | Kevin Roast | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3227 | Phone tab in Contact details does not display phone details | Kevin Roast | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3374 | Null Pointer Exeption generated from account AUM after timeout. | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3214 | Concurrent working warning absent in Dynacrud accounts after save | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3075 | Edit exisitng employee - timeout gives access to any login | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5 | 0
2890 | Account change to AUM value is not shown on summary after save | Kevin Roast | Q3 | 3 - Could | 2 | In Development | 1 | 0 | 0 | 1 | 1 | 0
3376 | Account shows labels for Company Entity and Buys | Kevin Roast | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
2948 | Filter for LOV editor | Kevin Roast | TBD | 3 - Could | 1.2.2 | In Development | 0.25 | 0 | 0 | 0.25 | 0.25 | 0
3198 | Edit Opening AUM - Value entered in timed out session submitted | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3446 | Finalise eventing documentation | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 2 | 0 | 0 | 2 | 2 | 0
3835 | Timeout on Content Library Wiz causes Object Ref Not Set error | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3622 | New DynaCRUD grid list grouping support | Kevin Roast | V2C3 | 3 - Could | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3632 | Answer Selector - Update to latest content model | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 2 | 0.5 | 0 | 0.5 | 2 | 1.5
2265 | Adding a Company - Instead of subsidiaries it would be better to attach Parent | Kevin Roast | TBD | 3 - Could | 1.2.2 | In Development | 1 | 0 | 0 | 1 | 1 | 0
3654 | When listing the opportunity size in the grid, we don't need pence shown! | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3873 | Edit Existing Employee - changes are not shown in Select Employee | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3874 | Account CRUD - Summary and Details screens are too large | Kevin Roast | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3887 | Subsidiaries is misspelt as Subsiduaries in Edit Company | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3673 | Company Joiners and Leavers not displayed due to MQL error | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3809 | New Topic - can set 'next review date to be in the past. | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
2399 | Add new emplyee from the team update dialog | Kevin Roast | TBD | 3 - Could | 1.2.2 | In Development | 2 | 0 | 0 | 2 | 2 | 0
3108 | Modifying enums can cause errors with existing sessions | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
1742 | Tree folders that should display a [+] do not after a login-as | Kevin Roast | Q3 | 2 - Should | 1.2.2 | In Development | 0.5 | 0 | 0 | 0.5 | #N/A | #N/A
3847 | Client HubModel display label resolution is broken. | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0.25 | 0.25 | 0 | 0.25 | 0.25 | 0
3849 | Account AUM inline editing does not show correct edit value in dropdown | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0.25 | 0.25 | 0 | 0.25 | 0.25 | 0
3242 | Add or edit investment service - vehicle selection is not possible | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3241 | Object ref not set - adding investment service to service package after timeout | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3240 | Can add/edit service package and investment service after timeout | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3858 | Canned queries - searches UI | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 2 | 0
3860 | Content Topic - Save Clone and copy content | Kevin Roast | V2C3 | 2 - Should | 2 | In Development | 2 | 2 | 0 | 2 | 2 | 0
3865 | CDB Template Question set tasks must come into view when required | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3872 | Edit existing employeeis not bringing back details from ety_employee | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3810 | New Topic - Business Area field overlaps unter it's selector button | Kevin Roast | V2C3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3609 | Topic content item - Summary Panels | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 2 | 1 | 0 | 1 | 2 | 1
2609 | Client config files cause unreported client failure | Kevin Roast | Q3 | 3 - Could | 2 | In Development | 0.5 | 0 | 0 | 0.5 | #N/A | #N/A
2457 | Output of Macros could have a nicer look to the table and better font choice etc | Kevin Roast | TBD | 3 - Could | 1.2.2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5 | 0
2706 | Could the exchange rate date range default to the end of the previous quarter. | Kevin Roast | TBD | 3 - Could | 1.2.2 | In Development | 0.25 | 0 | 0 | 0.25 | 0.25 | 0
3606 | Topic content item - Where Used Panel | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 1 | 0 | 0 | 1 | 1 | 0
3607 | Topic content item - History Panel | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 2 | 0
3652 | display panel should scroll to show details entered, or info should fit... | Linton Baddeley | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3651 | optional enum picker (hierarchical). Revisit. | Linton Baddeley | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3685 | Dashboard does not refresh automatically if changes are made in the Word plug-in | Nigel Dore | D2C | 1 - Must | 1.2.1 RFP Demo | In Development | 0.75 | 0.75 | 0 | 0.75 | 0.75 | 0
2522 | Percentages calculated differently | Nigel Dore | TBD | 2 - Should | 1.2.2 | In Development | 1 | 0 | 0 | 1 | 1 | 0
3745 | Plugin : Show additional opportunity details | Nigel Magnay | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3464 | Uninstall does not delete the empty mapper folders | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0 | -0.5
3747 | Plugin : Opportunity Workflow additions | Nigel Magnay | V2C3 | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 2 | 0
3846 | Runtime model deployment fails | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 1.5 | 1.5 | 0 | 1.5 | 0 | -1.5
3839 | Bootstrap data incudes incorrect Benchmarks.xls | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0 | -0.5
3417 | Concurrent use deletion of product allows error on add person or add vehicle | Nigel Magnay | Q3 | 2 - Should | 2 | In Development | 1 | 1 | 0 | 1 | #N/A | #N/A
3360 | Validate and Publish failure gives 404 error for report | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | #N/A | #N/A
2085 | Edit Existing Employee Start Date can be set after end date for all roles | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0 | -0.5
3744 | Plugin : Capability to change status | Nigel Magnay | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3365 | Install files only does not create ServiceDB directory in ItemField | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0.1 | 0.1 | 0 | 0.1 | 0 | -0.1
3378 | Concurrent modification of Service Package for account is not allowed | Nigel Magnay | Q3 | 2 - Should | 2 | In Development | 1 | 1 | 0 | 1 | 0 | -1
3469 | Diagnose error dialog box will not resize | Nigel Magnay | Q3 | 2 - Should | 2 | In Development | 0.2 | 0.2 | 0 | 0.2 | #N/A | #N/A
3631 | Hub Install - exctract Zip target fails = install failure | Nigel Magnay | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0 | -0.5
3861 | Application Initialisers must be called in a transaction | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | #N/A | #N/A
3635 | Plugin: View usage notes action | Nigel Magnay | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3215 | Changing fund for account; fails with integrity warning in concurrent use | Nigel Magnay | Q3 | 2 - Should | TBD | In Development | 0.5 | 0.5 | 0 | 0.5 | #N/A | #N/A
3819 | V2 Installation packages - creation from continuous build | Nigel Magnay | V2C3 | 1 - Must | 2 | In Development | 4 | 1 | 0 | 1 | 4 | 3
3216 | Problems with use of Continuous Build for deployment | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0.1 | 0.1 | 0 | 0.1 | 0 | -0.1
3719 | False Concurrent Modification warning on Link Strategy | Nigel Magnay | Q3 | 2 - Should | 2 | In Development | 1 | 1 | 0 | 1 | #N/A | #N/A
2827 | 'Resolve Conflicts' dialog - UI issues and cannot select checkbox | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0 | -0.5
3655 | Hub install issues with 'oracle-create-product-tables' and 'oracle-create-fts-pr | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 1.5 | 1.5 | 0 | 1.5 | 0 | -1.5
3838 | Maven directory included in the build | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0.1 | 0.1 | 0 | 0.1 | #N/A | #N/A
2344 | No validation of Employee dates | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 0 | -1
3174 | Hub files uninstall failure when using remote Itemfield. | Nigel Magnay | Q3 | 2 - Should | 2 | In Development | 0.25 | 0.25 | 0 | 0.25 | #N/A | #N/A
3204 | Files only install does not publish itemfield mappers. | Nigel Magnay | Q3 | 2 - Should | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | #N/A | #N/A
3864 | Create installation package for client including plug-in | Nigel Magnay | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3460 | Installation scripts used to load customer data add Malthill by default | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0.1 | 0.1 | 0 | 0.1 | 0 | -0.1
3837 | Limitation in Plain Text content size to 2048 chars | Paul Holmes-Higgin | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
1604 | Apparently unused enum in model? | Paul Holmes-Higgin | Q3 | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3662 | Edit Product default selection is Dead instead of Pilot | Paul Holmes-Higgin | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3706 | Model Cleanup - Remove unused components | Paul Holmes-Higgin | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3619 | Pointless question on Opportunity documents screen | Paul Holmes-Higgin | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3361 | Typo in the enum label for Investment Constraint | Paul Holmes-Higgin | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3411 | Can open multiple wizards from the RFP dialog which is confusing. | Paul Holmes-Higgin | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3370 | Employee Roles for: Company, Team, Strategy and Product- with No role | Paul Holmes-Higgin | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3626 | Hierarchy enum definitions loaded as flat | Paul Holmes-Higgin | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3113 | Model contains enumerated attributes that are not mandatory | Paul Holmes-Higgin | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3079 | CDB protected against editing change to CDB but not template changes | Paul Holmes-Higgin | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3878 | Item selector used in Client and Fund is not the same... | Paul Holmes-Higgin | V2C3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
2259 | Terminology for adding an office not appropriate | Paul Holmes-Higgin | TBD | 2 - Should | TBD | In Development | 2 | 0 | 0 | 2 | 2 | 0
3226 | Office DynaCrud does not distinguish external and internal offices | Paul Holmes-Higgin | V2C3 | 2 - Should | TBD | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3405 | Drag and Drop of answer should work from text or icon | Paul Holmes-Higgin | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
1885 | Employy CRUD - no help to change role - terminate employment | Paul Holmes-Higgin | TBD | 2 - Should | TBD | In Development | 1 | 0 | 0 | 1 | 1 | 0
3831 | Product Shortcut appears blank when created from Benchmark allocation | Paul Holmes-Higgin | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3832 | Edit Product from Benchmark allocation - details are blank | Paul Holmes-Higgin | V2C3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3237 | Validation reports only show the last validation | Paul Holmes-Higgin | TBD | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
2857 | Should maintain activiti tree structure when switching published /staging view | Paul Holmes-Higgin | V2C3 | 2 - Should | 2 | In Development | 2 | 0 | 0 | 2 | 2 | 0
3834 | Edit Target - dialog range warning refers to Target value but does not check it. | Richard Hodges | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3026 | Office - contact details - more infor to describe association | Richard Hodges | TBD | 3 - Could | 1.2.2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
1253 | Wizard continued after login on Session timeout while executing J/L wizard. | Richard Hodges | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
2788 | Wizards are orientated to power users and should/could be simplified | Richard Hodges | TBD | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3578 | Enable wizards to insert the results directly into Word | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
2782 | saving standard answer, should be able to see the summarised view of the crieria | Richard Hodges | TBD | 3 - Could | 2 | In Development | 0.75 | 0 | 0 | 0.75 | 0.75 | 0
2781 | Would be nice to have a button to skip directly to the layout page | Richard Hodges | TBD | 3 - Could | 2 | In Development | 0.3 | 0 | 0 | 0.3 | 0.3 | 0
2780 | Some of the detailed filter attributes are not product type sensitive | Richard Hodges | TBD | 3 - Could | 1.2.2 | In Development | 2 | 0 | 0 | 2 | 2 | 0
2778 | The wizards should display some context information about the stage you are in | Richard Hodges | TBD | 3 - Could | 1.2.2 | In Development | 0.75 | 0 | 0 | 0.75 | 0.75 | 0
3773 | Pivot Table - Settings forms | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 2 | 0.1 | 0 | 0.1 | 0.25 | 0.15
3862 | Edit Target - dialog range warning uses differing terminology to main screen | Richard Hodges | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3577 | Plugin: Call wizards from main menu | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3171 | Role display in client should be tidied | Richard Hodges | Q3 | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
2772 | Product Filters on the list are off the botton of the screen | Richard Hodges | TBD | 3 - Could | 1.2.2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5 | 0
3884 | The whole of PIM needs to be looked at for externalised Display Labels | Richard Hodges | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
2779 | The wizard order is not necessarily intuative | Richard Hodges | TBD | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
2566 | Add default parameter values when adding answers to templates/CDB | Richard Hodges | TBD | 2 - Should | 1.2.2 | In Development | 1.5 | 0 | 0 | 1.5 | 1.5 | 0
3623 | Employee Details screen - display lables taken from Model | Richard Hodges | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3628 | Exchange rate mapper and data load | Richard Hodges | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3451 | Documentation (Virtual hub model, Importers, Exporters, Recordset format) | Richard Hodges | Q3 | 1 - Must | 2 | In Development | 1 | 0 | 0 | 1 | 1 | 0
3506 | OLAP XML- HTML | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3442 | ClientIdentifier for Genericemployee should be returned to the UI | Richard Hodges | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3441 | Errors in loading of employee data | Richard Hodges | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
2887 | Index rebuild is not building partition indexes correctly | Richard Hodges | TBD | 2 - Should | 1.2.2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5 | 0
3428 | Service Package is essential to AUM product route but change not picked up | Richard Hodges | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
1891 | Wizards - dates in fixed order | Richard Hodges | TBD | 3 - Could | 1.2.2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5 | 0
2558 | Product Management Locations in PIM Product Wizard should show company | Richard Hodges | Q3 | 1 - Must | 2 | In Development | 1 | 0 | 0 | 1 | 1 | 0
3780 | Date Selection Screen - new version | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1.5 | 0.1 | 0 | 0.1 | 1.5 | 1.4
3666 | Employee to Product, Strategy and Team mapper - amend to include ID | Richard Hodges | Q2 | 1 - Must | 2 | In Development | 0.25 | 0.25 | 0 | 0.25 | 0.25 | 0
3803 | Save Exporter - XML format exporter for save | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1 | 0.1 | 0 | 0.1 | 0.1 | 0
3790 | Define remaining six wizards - Build DynaCrud XML definition | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1.5 | 1.5 | 0 | 1.5 | 1.5 | 0
3800 | UI inspection - Inspect and fix | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1 | 0.75 | 0 | 0.75 | 1 | 0.25
3798 | Performance Tuning - Test and Fix | Richard Hodges | V2C3 | 2 - Should | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3797 | Product Selection- Adding to the Generic Filter Control | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1.5 | 0.1 | 0 | 0.1 | 0.25 | 0.15
3796 | Integration Testing | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1.5 | 1.5 | 0 | 1.5 | 1.5 | 0
3795 | Wizard Selector - Update Wizard Enum, Launch, Edit | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3792 | Wizard Selector- Configuration File | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3778 | Date Selection Screen - old version | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.1 | 0 | 0.1 | 0.1 | 0
3789 | Table Support in XML - Import Support for Aggregate Tables | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3786 | Table Support in XML - Export Support for Aggregate Tables | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.1 | 0 | 0.1 | 0.1 | 0
3784 | Summary Screen - Task Summary | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3783 | Summary Screen - Preview Rendering | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.1 | 0 | 0.1 | 0.5 | 0.4
3793 | Wizard Selector - New wizard | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
2279 | There is no quick way of copying people from one strategy to another , instead t | Roy Wetherall | TBD | 3 - Could | 1.2.2 | In Development | 5 | 0 | 0 | 5 | 5 | 0
1551 | Short cut - product inconsistent | Roy Wetherall | Q3 | 3 - Could | 2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5 | 0
1900 | New Strategies and Products added are not sorted in the tree | Roy Wetherall | Q3 | 3 - Could | 2 | In Development | 1 | 0 | 0 | 1 | 1 | 0
3573 | Plugin: Canned search queries | Roy Wetherall | V2C3 | 2 - Should | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3642 | If you put a value in (e.g for size), you must enter a currency | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3830 | Benchmark allocation- multiple additions on correcting min/max violation | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3829 | Constraint tasks, available inappropriately => errors with deleted constraint | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3828 | Edit product may retreive incorrect version on edit | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3653 | If you click on the checkbox next to a vehicle it should highlight it.... | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3649 | scheme type only enabled if fund type is pension | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3567 | Plugin: Search options UI | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3643 | Add a 'view details' option when adding people | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3674 | Vehicle allocation Grid columns have no titles | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3641 | Currency: should be able to specify units (millions, etc) | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3639 | Typo - specify spelt wrong | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3624 | No confirmation when Cancelling the creation of a new Opp | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3620 | New Opp, Fund Information, 'Specify existing fund' - existing funds not shown | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3618 | Rounding error for Cash Flow in a New Opp, | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3617 | Summary screen - long text wraps and is obscured | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3644 | Date Validation: Internal Deadline >= Date Received. | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3833 | Edit Target for product - dialog behaviour is inconsistant. | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3882 | Opportunities - itmes that do not have externalised display labels | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3880 | Error scrolling through Joiners/Leavers for 2002 by company | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3859 | Errors deleting doc. from Opportunity where multiple docs have the same name | Roy Wetherall | V2C3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3852 | Edit Target dialog - empty fields are allowed. | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3851 | Edit Target dialog - non numeric input generates imprecise warning | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3850 | Edit Target dialog - warning wording should be changed. | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3857 | Adding different docs to opportunity with the same name results in overwriting | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3836 | New Opp Wizard - Step 7 page is too large for dialog | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3667 | & character does not disply in the Benchmark Allocation details dialog | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3823 | Moving different strategy links to same sub folder - error message is wrong. | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3812 | Can create multiple icons for the same strategy at root level | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3811 | Clone product and clone vehicle give class cast exception | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3750 | Delete product in published or staging area causes class cast exception | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3746 | Plugin : Save as Standard | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 3 | 3 | 0 | 3 | 3 | 0
3614 | Wizard details on LHS do not scorll or size to length of details list | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3845 | PIM Tree node should be removed from the Staging 'Preview Work Area' | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3407 | Searching by Selecting text from Within question and right click | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3616 | when you are in the opportunities grid 'Copy to Clipboard' copies wrong info | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3718 | Link Person to product (or strategy) gives MQL error | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3700 | Plugin doesn't start but causes an error starting Word- Infragistics reference | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3429 | Vehicle wizard - identifiers display is too small | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A | #N/A
3422 | Failure of Product edit without error | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3420 | Change Staging Area - NewProduct's Manufacturing company- Nullpointer error | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3550 | Plugin: Human readable tags | Roy Wetherall | V2C3 | 2 - Should | 2 | In Development | 1 | 0.01 | 0 | 0.01 | 1 | 0.99
3408 | Need Control of Graphics on Paste into Document | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3555 | Plugin: Content I'm Editing Grid | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3402 | Opportunity Field , shoud display opportunity name as the label | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3416 | Shortcut use after deletion of product by other client gives error as pt 2957 | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3232 | Strategy can have a start date after the end date | Roy Wetherall | Q3 | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3210 | Edit person - questionable selection of office for individual from history | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3189 | Strategy Roles mapper does not maintain date order of the roles in data | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3160 | Datalists in the CDB area (Companies and QSets below that) forget column widths | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3418 | Add product in a workarea locks product creation in published | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3579 | Plugin: Info map grid containing answers in the document | Roy Wetherall | Q2 | 1 - Must | 2 | In Development | 1 | 0 | 1 | 0 | 0 | 0
3247 | Word Plugin: Shared login | Roy Wetherall | V2C3 | 3 - Could | 2 | In Development | 3 | 3 | 0 | 3 | 3 | 0
3612 | Changing consultant in edit screen causes server error on import | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3592 | Plugin: Info map infomation panel | Roy Wetherall | V2C3 | 3 - Could | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3591 | Plugin: Apply Word macro's to formating of tables upon insert from wizard | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 1 | 0.5 | 0 | 0.5 | 1 | 0.5
3589 | Plugin: Opp details status panel | Roy Wetherall | V2C3 | 3 - Could | 2 | In Development | 1 | 1 | 0 | 1 | 1 | 0
3588 | Plugin: Opp details information panel | Roy Wetherall | V2C3 | 3 - Could | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3720 | Link Products to Strategy dialog typo - misses word select in dialog description | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3581 | Plugin: Info map, "Refresh answer" action | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3615 | timed out on the Opportunities grid gives error | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0 | 0
3574 | Plugin: Insert answer action | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.1 | 1.5 | 0.1 | 0 | -0.1
3571 | Plugin: Search "View realted items" action | Roy Wetherall | V2C3 | 2 - Should | 2 | In Development | 1.5 | 1.5 | 0 | 1.5 | 1.5 | 0
3566 | Plugin: Search context UI | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3561 | Plugin: "Print" action | Roy Wetherall | V2C3 | 3 - Could | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3560 | Plugin: "Save As" task | Roy Wetherall | V2C3 | 3 - Could | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3559 | Plugin: "Save as external copy" task | Roy Wetherall | V2C3 | 2 - Should | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0
3587 | Plugin: Information panel | Roy Wetherall | V2C3 | 3 - Could | 2 | In Development | 1.5 | 1.3 | 0 | 1.3 | 1.3 | 0

## PrevPTTasks
PRN | Title | Assigned To | Fix in Timebox | Timebox Priority | Required in Release | Status | Estimated Size | Remaining Effort | Actual Size | To Do | NewEstimate
3762 | Get Used attributes for macro and cube -> event support | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3799 | Initialise macros and answers | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.2 | 0 | 0.2 | 0.2
3794 | Expand by hierarchy for join - up and down | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.1
3791 | Hierarchy for joins via role in cube implementation | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3363 | Account with AUM closing value only showed up in the AUM wizard list | Andy Hind | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3788 | date population on the data base rather than MBean | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3785 | Indicate total to use for percentage calculations | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 0.2 | 0.2 | 0 | 0.2 | 0.2
3782 | Add formatting control to data column and roll ups | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1
3779 | Specify the name of the total roll up in groupings | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 0.2 | 0.2 | 0 | 0.2 | 0.2
3774 | Add index for date and fix existing additional indexes | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | #N/A
3772 | Add support to filter using like in attributes | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 1 | 1 | 0 | 1 | 1
3770 | Provide estimates of macro execution times to the user | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 2 | 2 | 0 | 2 | 2
3769 | Generate textual descriptions of macros | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 0.8
3768 | Indexes for macro performance | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 2 | 2 | 0 | 2 | 2
3802 | Wizard rendering and save integration | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | #N/A
3754 | Definitions for the Joiners/Leavers cube | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
2687 | Wizards - as they are slow would like to be able to cancel | Andy Hind | V2C3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
2751 | Wizard Joiners and Leavers as at 2003 date when IP start today | Andy Hind | Q3 | 1 - Must | 2 | In Development | 1 | 0 | 0 | 1 | 1
2754 | Office start date not being used in Pivot table as at date | Andy Hind | Q3 | 1 - Must | 2 | In Development | 2 | 0 | 0 | 2 | 2
3514 | Count of Joiners Leavers does unique count for individual | Andy Hind | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3504 | OLAP- Cube definition for personnel | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 1 | 0.3 | 0 | 0.3 | 0.1
3767 | Macros - support adding missing enums to roll ups (blanks) | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 2 | 2 | 0 | 2 | 2
3753 | Unit tests for the macro framework | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 2 | 2 | 0 | 2 | 2
3764 | Port the investment professionals macros (9) | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 0.5
3755 | Function definitions for the joiners leavers cube | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1
3756 | Add cube definitions for new/lost | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3757 | Functions for new lost cube | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1
3758 | Cube definition for company wide joiners and leavers | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3761 | Macro Events - predicate use | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 2 | 2 | 0 | 2 | 2
3765 | port company wide joiners leavers macros (1) | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 0.3 | 0.3 | 0 | 0.3 | 0.3
3752 | Performance tests for the macro framework | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 1 | 1 | 0 | 1 | 1
3763 | Macro ports for N/L (9) | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 1.5 | 1.5 | 0 | 1.5 | 1.5
3804 | Add id and provide to amcro definitions as loaded if missing | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 0.2 | 0.2 | 0 | 0.2 | 0.2
3807 | Ordering functions for grouping | Andy Hind | V2C3 | 3 - Could | 2 | In Development | 1 | 1 | 0 | 1 | 1
3805 | Regression test remainaing macros | Andy Hind | V2C3 | 1 - Must | 2 | In Development | 1.5 | 1.5 | 0 | 1.5 | 1.3
3821 | Create BAT tests for new V2 functionality | Anne Whitty | V2C3 | 1 - Must | 2 | In Development | 3 | 3 | 0 | 3 | 3
3822 | Update existing BAT documents for V2.0 | Anne Whitty | V2C3 | 1 - Must | 2 | In Development | 5 | 5 | 0 | 5 | 5
147 | Cannot specify type or attribute names that are reserved database words | David Caruana | TBD | 3 - Could | TBD | In Development | 0 | 0 | 0 | 0 | 0
3465 | Fix Integrity issues fails - unable to find HubSupportService | David Caruana | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
1794 | Register and eventing should interact on entity deletions | David Caruana | Q3 | 3 - Could | 1.2.2 | In Development | 2 | 0 | 0 | 2 | 2
3734 | Conformance: Engine: Rule Locking | David Caruana | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.1
3827 | Edit product creates two new versions on each edit | David Caruana | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3278 | Events: Cleanup ChangeStack and remove old events framework | David Caruana | V2C3 | 3 - Could | 2 | In Development | 2 | 0 | 0 | 2 | 1
146 | Cannot create entities with no attributes | David Caruana | Q3 | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0
3693 | Database Profile of Create Workarea, Import Data, Remove Workarea & Repeat | David Caruana | Q2 | 1 - Must | 2 | In Development | 1 | 0 | 0 | 1 | 1
3434 | Attributed Aggregated associations not visible in DDClass | David Caruana | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
941 | DDClass getOperations() - wrong for soft type | David Caruana | Q3 | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0
2543 | Cannot specify domicile for employee in the UI | David Caruana | TBD | 1 - Must | TBD | In Development | 0 | 0 | 0 | 0 | 0
3848 | Specifically reference an assoc in an MQL statement and not return it crashes | David Caruana | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3725 | Conformance: Engine: Transaction based events and execution context | David Caruana | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5
3629 | Bridge table type needs all relationships | David Caruana | Q3 | 1 - Must | TBD | In Development | 0 | 0 | 0 | 0 | 0
3741 | Conformance: Admin: Conformance JMX Bean | David Caruana | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0 | 0 | 0.5 | #N/A
3731 | Conformance: Appl. Integration: Port Rules (Office, AUM) | David Caruana | V2C3 | 1 - Must | 2 | In Development | 2 | 0 | 0 | 2 | 0.1
3739 | Conformance: Appl. Integration: Port Validation Macros to Rules | David Caruana | V2C3 | 1 - Must | 2 | In Development | 1 | 0 | 0 | 1 | 1
3738 | Conformance: Appl. Integration: Port Rules (Remaining) | David Caruana | V2C3 | 1 - Must | 2 | In Development | 2 | 0 | 0 | 2 | 2
3698 | Workarea service should be doing business logic checks | David Caruana | V2C3 | 1 - Must | 2 | In Development | 2 | 0 | 0 | 2 | 2
3627 | AUM validation macos - do not use account identifier functions | David Caruana | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3777 | Missing staging area cm index on associations and roles | David Caruana | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
1371 | XResultSet API needs refactoring | David Caruana | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3625 | Inserts or updates of data into the hub cause the client to hang | David Caruana | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
2852 | Some changes to product features allowed for 'locked' entity. | David Caruana | TBD | 1 - Must | TBD | In Development | 0 | 0 | 0 | 0 | 0
3815 | Publish single entity in workarea | David Caruana | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
1226 | No way of defining indexes for attribute on associations | David Caruana | TBD | 3 - Could | TBD | In Development | 0 | 0 | 0 | 0 | 0
1324 | IDs not treated uniquely between staging areas | David Caruana | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3375 | Account on QA filprod causes infinite loop on save | David Caruana | Q3 | 1 - Must | 1.2.2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5
3813 | Draft content workarea at bootstrap | David Caruana | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3145 | Vehicle Identifiers do not have to be unique within datasource | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3243 | Deletion of entities does not check the staging area | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3471 | Integrity errors in Employee import validation | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3470 | Integrity errors in AUM import validation | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
2257 | Copying questions would a useful feature. | Derek Hulley | TBD | 3 - Could | 1.2.2 | In Development | 1 | 0 | 0 | 1 | 1
1768 | Icons in the grid for workareas do not change to reflect there status. | Derek Hulley | Q3 | 2 - Should | 2 | In Development | 0.25 | 0 | 0 | 0.25 | 0.25
3733 | Conformance: Events: Staging Area Lifetime Events | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 2 | 0 | 0 | 2 | #N/A
2337 | CDB Template does not display a column for question set type | Derek Hulley | Q3 | 2 - Should | 2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5
3520 | dbValidate Null pointer on build 282 | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3521 | dbValidate errors with association class | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
2661 | CDB Template New Question set dialog should not close after adding question set | Derek Hulley | TBD | 3 - Could | 1.2.2 | In Development | 1.5 | 0 | 0 | 1.5 | 1.5
3705 | Model Cleanup - Remove unused components | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 1.5 | 1.5 | 0 | 1.5 | 1.5
2480 | Employee mapper should be updated - include email address | Derek Hulley | TBD | 3 - Could | 1.2.2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5
2518 | Translator mechanism in mappers issue | Derek Hulley | TBD | 3 - Could | 1.2.2 | In Development | 3 | 0 | 0 | 3 | 3
3078 | CDB mark all as updated warning dialog is same for outdated | Derek Hulley | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3656 | Validation fails for Fidelity Q2 data | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3863 | Write MQL for Canned Queries | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 0.75 | 0.75 | 0 | 0.75 | 0.75
1490 | Can't copy/clone a question set | Derek Hulley | TBD | 3 - Could | 1.2.2 | In Development | 1 | 0 | 0 | 1 | 1
3661 | Itemfield unit tests to be based on checking of intermediate xml | Derek Hulley | Q2 | 1 - Must | 2 | In Development | 2 | 0.5 | 0 | 0.5 | 0.5
2531 | Focus of CDB grid is not maintained after edits, etc. | Derek Hulley | TBD | 3 - Could | 1.2.2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5
3522 | Validate and Publish gave failure and 404 and 500 errors displaying the report | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3362 | Typo in the error output from db-vallidate | Derek Hulley | Q3 | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0
2255 | Cannot associate a consultant company to a CDB. | Derek Hulley | TBD | 1 - Must | TBD | In Development | 1 | 0 | 0 | 1 | 1
3299 | Cannot set an end date for office with no employees | Derek Hulley | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3817 | View content version method | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.25
3816 | Content history method | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.25
3419 | Adding a product in a workarea produces validation error | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3396 | Full Text Search of information in table fails to match | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3735 | Conformance: Engine: Staging Area based events and execution context | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 1 | 0 | 0 | 1 | 0.5
2907 | Import of specific CDB macro fails due to case sensitive title | Derek Hulley | Q3 | 2 - Should | 2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5
3630 | Item field pre-parser rounding <data> tag entry | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 1 | 0 | 0 | 1 | 1
3352 | Migration Analysis Core Content | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3351 | Migration Analysis Macros | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3350 | Migration Analysis CDB | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3349 | CDB Test UI | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 1 | 0.5 | 0 | 0.5 | 0.5
3348 | CDB UI Code Fixes | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 2 | 0.5 | 0 | 0.5 | 0.25
3343 | Answer Selector Test UI | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 0.25 | 0.25 | 0 | 0.25 | 0.25
3801 | Validation error | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3386 | Concurrent use - Mapper for import can be changed in UI after import | Derek Hulley | Q3 | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0
3196 | No CDB concurrancy use warning when answer status is being updated | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3468 | Fix Integrity issues should only be available to admin user | Derek Hulley | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3737 | Conformance: Appl. Integration: Workarea Integration | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 3 | 0 | 0 | 3 | 3
3467 | Validation report Integrity issues are shown with an intity ID GUID | Derek Hulley | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3462 | Loss of database connection after validating workarea | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3342 | Answer Selector UI Code | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 0.25 | 0.25 | 0 | 0.25 | #N/A
3456 | Content webservices/manager etc - stress and performance testing | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 2 | 0 | 0 | 2 | 2
3238 | Import mapper errors against incorrect import file type. | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3005 | Can add AUM values to Closed accounts after the end date | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5
3199 | CDB concurrent use error - delete product during export answers | Derek Hulley | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3202 | Error hidden on Export Answers fail with missing currency conversion | Derek Hulley | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3759 | Eventing suport for macros at the entity/attribute layer | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 2 | 1 | 0 | 1 | 1
3760 | Events for time periods end of month, quarter, year | Derek Hulley | V2C3 | 1 - Must | 2 | In Development | 0.25 | 0.25 | 0 | 0.25 | #N/A
2994 | Export answers threw error with a word document in sharepoint open | Derek Hulley | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3213 | Investment Target Mapper only works with equity products | Derek Hulley | V2C3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3066 | Employee validation required to ensure name is equivalent to forename surname | Gav Cornwell | Q3 | 2 - Should | 2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5
3444 | Edit fails for csv file in workarea - changes are not saved. | Gav Cornwell | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3613 | Adding file of the same name can be uploaded onto the WebDav server, causes an e | Gav Cornwell | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3426 | Errors traced out to hub console should be better handled | Gav Cornwell | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3702 | Enable Activiti Client for On-line Help | Gav Cornwell | V2C3 | 1 - Must | 2 | In Development | 3 | 3 | 0 | 3 | #N/A
3458 | Examine error gives 404 trying to access /diagnostics/error/index.jsp | Gav Cornwell | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3137 | After timeout in the admin console I can not launch the JMX console | Gav Cornwell | Q3 | 3 - Could | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3824 | Transaction not allowed error during IntegrationService System Test | Gav Cornwell | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3636 | Plugin: Asnwer details on the doc info panel | Gav Cornwell | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1
3637 | Plugin: Answer tasks to appear on the answer doc info panel | Gav Cornwell | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1
3696 | Public AuthenticationService does not have logout method | Gav Cornwell | Q3 | 1 - Must | 2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5
3709 | CDB - Implement rendering | Gav Cornwell | V2C3 | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 2
3710 | CDB - Answer Preview Integration | Gav Cornwell | V2C3 | 1 - Must | 2 | In Development | 0.25 | 0.25 | 0 | 0.25 | 0.25
3711 | CDB - Final integration test (does it all work) | Gav Cornwell | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3708 | CDB - Hook up the answer selector | Gav Cornwell | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1
3676 | AIX Port: Regression Test | Jan Vonka | V2T | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 2
3677 | AIX Port: Installer / Uninstaller | Jan Vonka | V2T | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 2
3668 | Integrate new test data into head and continuous build | Jan Vonka | V2C3 | 1 - Must | 2 | In Development | 4 | 2 | 0 | 2 | 1.5
3212 | JMX pages in admin console need to be made generic | Jan Vonka | Q3 | 2 - Should | 2 | In Development | 2 | 0 | 0 | 2 | 2
3729 | Conformance: Register: Register Transaction Class | Jan Vonka | V2C3 | 1 - Must | 2 | In Development | 2 | 0 | 0 | 2 | 2
3730 | Conformance: Appl. Integration: DynaCRUD Integration | Jan Vonka | V2C3 | 1 - Must | 2 | In Development | 1 | 0 | 0 | 1 | 1
3675 | AIX Port: Setup Server Environment for WAS | Jan Vonka | V2T | 1 - Must | 2 | In Development | 2 | 0.5 | 0 | 0.5 | 0.5
3740 | Conformance: Admin: Hub Conformance Utility | Jan Vonka | V2C3 | 1 - Must | 2 | In Development | 1 | 0 | 0 | 1 | 1
3288 | Websphere Port: Port Web Services | Jan Vonka | Q2 | 1 - Must | 2 | In Development | 3 | 0.5 | 0 | 0.5 | 0.5
3289 | Websphere Port: Fix Compliance Issues | Jan Vonka | V2T | 1 - Must | 2 | In Development | 3 | 0.5 | 0 | 0.5 | 0.5
3290 | Websphere Port: Port JMX Usage | Jan Vonka | V2T | 2 - Should | 2 | In Development | 1 | 1 | 0 | 1 | 1
3291 | Websphere Port: Continuous Build Process | Jan Vonka | V2C3 | 1 - Must | 2 | In Development | 3 | 2 | 0 | 2 | 0.5
3292 | Websphere Port: Regression Test | Jan Vonka | V2T | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 2
3293 | Websphere Port: Installer / Uninstaller | Jan Vonka | V2T | 1 - Must | 2 | In Development | 2 | 4 | 0 | 4 | 4
3294 | Websphere Port: JBoss 3.2 Compatibility | Jan Vonka | V2T | 3 - Could | 2 | In Development | 1 | 1 | 0 | 1 | 1
3295 | Websphere Port: Port JMS Usage | Jan Vonka | V2T | 1 - Must | 2 | In Development | 1 | 0.5 | 0 | 0.5 | 0.5
3296 | Websphere Port: Port Configuration Services | Jan Vonka | V2T | 3 - Could | 2 | In Development | 1 | 1 | 0 | 1 | 1
3736 | Conformance: Engine: Hub based execution context | Jan Vonka | V2C3 | 1 - Must | 2 | In Development | 1 | 0 | 0 | 1 | 1
3858 | Canned queries - searches UI | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 2
3225 | Adding Office cannot determine external or internal office | Kevin Roast | Q3 | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0
3376 | Account shows labels for Company Entity and Buys | Kevin Roast | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3605 | Context Edit pull down panel | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 1 | 0.5 | 0 | 0.5 | #N/A
3325 | UI Parameters Wizard - UI Implementation Code | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 2 | 0.5 | 0 | 0.5 | 0.5
3606 | Topic content item - Where Used Panel | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 1 | 0 | 0 | 1 | 1
3607 | Topic content item - History Panel | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 2
3608 | Topic content item - Preview Panel | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | #N/A
3609 | Topic content item - Summary Panels | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 1
3379 | Company Entity for account allows duplicates and no roles for company | Kevin Roast | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3108 | Modifying enums can cause errors with existing sessions | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3596 | Inline actions available in the new DynaCRUD UltraGrid impl | Kevin Roast | Q2 | 1 - Must | 2 | In Development | 2 | 0.5 | 0 | 0.5 | #N/A
3023 | Deleting value form the LOV editor - in use notification does not detail object | Kevin Roast | Q3 | 2 - Should | 2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5
3835 | Timeout on Content Library Wiz causes Object Ref Not Set error | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3401 | Double Click enabled for Dynacrud Selection Lists | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
2890 | Account change to AUM value is not shown on summary after save | Kevin Roast | Q3 | 3 - Could | 2 | In Development | 1 | 0 | 0 | 1 | 1
3242 | Add or edit investment service - vehicle selection is not possible | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3214 | Concurrent working warning absent in Dynacrud accounts after save | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3446 | Finalise eventing documentation | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 2 | 0 | 0 | 2 | 2
3240 | Can add/edit service package and investment service after timeout | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
2948 | Filter for LOV editor | Kevin Roast | TBD | 3 - Could | 1.2.2 | In Development | 0.25 | 0 | 0 | 0.25 | 0.25
3421 | Edit vehicle with two spaces threw error in confusion with 1 space version | Kevin Roast | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3228 | Label for the enums used in the UI should be usable to identify LOV entry | Kevin Roast | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | #N/A
3217 | concurrent Use warning persists after the user has finished using the record. | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3427 | Concurrent edit of account numbers missing warnings | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3622 | New DynaCRUD grid list grouping support | Kevin Roast | V2C3 | 3 - Could | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3673 | Company Joiners and Leavers not displayed due to MQL error | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3809 | New Topic - can set 'next review date to be in the past. | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
2399 | Add new emplyee from the team update dialog | Kevin Roast | TBD | 3 - Could | 1.2.2 | In Development | 2 | 0 | 0 | 2 | 2
2457 | Output of Macros could have a nicer look to the table and better font choice etc | Kevin Roast | TBD | 3 - Could | 1.2.2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5
3654 | When listing the opportunity size in the grid, we don't need pence shown! | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3318 | Account Details Copy view to clipboard only copies Company Entity Details | Kevin Roast | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3849 | Account AUM inline editing does not show correct edit value in dropdown | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0.25 | 0.25 | 0 | 0.25 | 0.25
3632 | Answer Selector - Update to latest content model | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 0.5
3847 | Client HubModel display label resolution is broken. | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0.25 | 0.25 | 0 | 0.25 | 0.25
3205 | Case for failure of concurrent modification warning | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3220 | New Mindmap locations after use are not properly deleted | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3860 | Content Topic - Save Clone and copy content | Kevin Roast | V2C3 | 2 - Should | 2 | In Development | 2 | 2 | 0 | 2 | 2
3221 | Adding new Office for internal company adds a blank line | Kevin Roast | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
2265 | Adding a Company - Instead of subsidiaries it would be better to attach Parent | Kevin Roast | TBD | 3 - Could | 1.2.2 | In Development | 1 | 0 | 0 | 1 | 1
3075 | Edit exisitng employee - timeout gives access to any login | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5
3001 | To-Do lists are avaiable in Admin role, should be suppressed | Kevin Roast | TBD | 3 - Could | 1.2.2 | In Development | 0 | 0 | 0 | 0 | 0
2706 | Could the exchange rate date range default to the end of the previous quarter. | Kevin Roast | TBD | 3 - Could | 1.2.2 | In Development | 0.25 | 0 | 0 | 0.25 | 0.25
3374 | Null Pointer Exeption generated from account AUM after timeout. | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3198 | Edit Opening AUM - Value entered in timed out session submitted | Kevin Roast | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3553 | Document preview view | Kevin Roast | V2C3 | 1 - Must | 2 | In Development | 1 | 0.5 | 0 | 0.5 | 0.5
3652 | display panel should scroll to show details entered, or info should fit... | Linton Baddeley | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3651 | optional enum picker (hierarchical). Revisit. | Linton Baddeley | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
2522 | Percentages calculated differently | Nigel Dore | TBD | 2 - Should | 1.2.2 | In Development | 1 | 0 | 0 | 1 | 1
3685 | Dashboard does not refresh automatically if changes are made in the Word plug-in | Nigel Dore | D2C | 1 - Must | 1.2.1 RFP Demo | In Development | 0.75 | 0.75 | 0 | 0.75 | 0.75
3464 | Uninstall does not delete the empty mapper folders | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0.5
3365 | Install files only does not create ServiceDB directory in ItemField | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0.1
3820 | Assistance with porting to AIX and Websphere | Nigel Magnay | V2T | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | #N/A
2827 | 'Resolve Conflicts' dialog - UI issues and cannot select checkbox | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0.5
3631 | Hub Install - exctract Zip target fails = install failure | Nigel Magnay | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0.5
3378 | Concurrent modification of Service Package for account is not allowed | Nigel Magnay | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 1
3819 | V2 Installation packages - creation from continuous build | Nigel Magnay | V2C3 | 1 - Must | 2 | In Development | 4 | 4 | 0 | 4 | 1
3655 | Hub install issues with 'oracle-create-product-tables' and 'oracle-create-fts-pr | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 1.5
3460 | Installation scripts used to load customer data add Malthill by default | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0.1
2344 | No validation of Employee dates | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 1
3853 | Hub initialisation levels fail quietly | Nigel Magnay | V2C3 | 1 - Must | 2 | In Development | 0.25 | 0.25 | 0 | 0.25 | #N/A
3846 | Runtime model deployment fails | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 1.5
3744 | Plugin : Capability to change status | Nigel Magnay | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3839 | Bootstrap data incudes incorrect Benchmarks.xls | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0.5
3745 | Plugin : Show additional opportunity details | Nigel Magnay | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
2085 | Edit Existing Employee Start Date can be set after end date for all roles | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0.5
3747 | Plugin : Opportunity Workflow additions | Nigel Magnay | V2C3 | 1 - Must | 2 | In Development | 2 | 2 | 0 | 2 | 2
3864 | Create installation package for client including plug-in | Nigel Magnay | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1
3635 | Plugin: View usage notes action | Nigel Magnay | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1
3216 | Problems with use of Continuous Build for deployment | Nigel Magnay | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0.1
3626 | Hierarchy enum definitions loaded as flat | Paul Holmes-Higgin | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
1604 | Apparently unused enum in model? | Paul Holmes-Higgin | Q3 | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0
2259 | Terminology for adding an office not appropriate | Paul Holmes-Higgin | TBD | 2 - Should | TBD | In Development | 2 | 0 | 0 | 2 | 2
1885 | Employy CRUD - no help to change role - terminate employment | Paul Holmes-Higgin | TBD | 2 - Should | TBD | In Development | 1 | 0 | 0 | 1 | 1
3361 | Typo in the enum label for Investment Constraint | Paul Holmes-Higgin | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3370 | Employee Roles for: Company, Team, Strategy and Product- with No role | Paul Holmes-Higgin | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3837 | Limitation in Plain Text content size to 2048 chars | Paul Holmes-Higgin | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3706 | Model Cleanup - Remove unused components | Paul Holmes-Higgin | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3405 | Drag and Drop of answer should work from text or icon | Paul Holmes-Higgin | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3237 | Validation reports only show the last validation | Paul Holmes-Higgin | TBD | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
2857 | Should maintain activiti tree structure when switching published /staging view | Paul Holmes-Higgin | V2C3 | 2 - Should | 2 | In Development | 2 | 0 | 0 | 2 | 2
3411 | Can open multiple wizards from the RFP dialog which is confusing. | Paul Holmes-Higgin | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3079 | CDB protected against editing change to CDB but not template changes | Paul Holmes-Higgin | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3113 | Model contains enumerated attributes that are not mandatory | Paul Holmes-Higgin | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3171 | Role display in client should be tidied | Richard Hodges | Q3 | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0
3862 | Edit Target - dialog range warning uses differing terminology to main screen | Richard Hodges | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3834 | Edit Target - dialog range warning refers to Target value but does not check it. | Richard Hodges | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3442 | ClientIdentifier for Genericemployee should be returned to the UI | Richard Hodges | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
2558 | Product Management Locations in PIM Product Wizard should show company | Richard Hodges | Q3 | 1 - Must | 2 | In Development | 1 | 0 | 0 | 1 | 1
3506 | OLAP XML- HTML | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3773 | Pivot Table - Settings forms | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 2 | 0.25 | 0 | 0.25 | 0.1
2781 | Would be nice to have a button to skip directly to the layout page | Richard Hodges | TBD | 3 - Could | 2 | In Development | 0.3 | 0 | 0 | 0.3 | 0.3
2780 | Some of the detailed filter attributes are not product type sensitive | Richard Hodges | TBD | 3 - Could | 1.2.2 | In Development | 2 | 0 | 0 | 2 | 2
2779 | The wizard order is not necessarily intuative | Richard Hodges | TBD | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0
2778 | The wizards should display some context information about the stage you are in | Richard Hodges | TBD | 3 - Could | 1.2.2 | In Development | 0.75 | 0 | 0 | 0.75 | 0.75
2772 | Product Filters on the list are off the botton of the screen | Richard Hodges | TBD | 3 - Could | 1.2.2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5
3803 | Save Exporter - XML format exporter for save | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1 | 0.1 | 0 | 0.1 | 0.1
2566 | Add default parameter values when adding answers to templates/CDB | Richard Hodges | TBD | 2 - Should | 1.2.2 | In Development | 1.5 | 0 | 0 | 1.5 | 1.5
3489 | Time Box Integration - Server side plug in | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1.25 | 0.5 | 0 | 0.5 | #N/A
3577 | Plugin: Call wizards from main menu | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3578 | Enable wizards to insert the results directly into Word | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1
3666 | Employee to Product, Strategy and Team mapper - amend to include ID | Richard Hodges | Q2 | 1 - Must | 2 | In Development | 0.25 | 0.25 | 0 | 0.25 | 0.25
3026 | Office - contact details - more infor to describe association | Richard Hodges | TBD | 3 - Could | 1.2.2 | In Development | 0 | 0 | 0 | 0 | 0
1891 | Wizards - dates in fixed order | Richard Hodges | TBD | 3 - Could | 1.2.2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5
3623 | Employee Details screen - display lables taken from Model | Richard Hodges | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3628 | Exchange rate mapper and data load | Richard Hodges | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
1253 | Wizard continued after login on Session timeout while executing J/L wizard. | Richard Hodges | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3790 | Define remaining six wizards - Build DynaCrud XML definition | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1.5 | 1.5 | 0 | 1.5 | 1.5
3800 | UI inspection - Inspect and fix | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 0.75
3798 | Performance Tuning - Test and Fix | Richard Hodges | V2C3 | 2 - Should | 2 | In Development | 1 | 1 | 0 | 1 | 1
3797 | Product Selection- Adding to the Generic Filter Control | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1.5 | 0.25 | 0 | 0.25 | 0.1
3796 | Integration Testing | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1.5 | 1.5 | 0 | 1.5 | 1.5
3795 | Wizard Selector - Update Wizard Enum, Launch, Edit | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1
2782 | saving standard answer, should be able to see the summarised view of the crieria | Richard Hodges | TBD | 3 - Could | 2 | In Development | 0.75 | 0 | 0 | 0.75 | 0.75
3792 | Wizard Selector- Configuration File | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3451 | Documentation (Virtual hub model, Importers, Exporters, Recordset format) | Richard Hodges | Q3 | 1 - Must | 2 | In Development | 1 | 0 | 0 | 1 | 1
3789 | Table Support in XML - Import Support for Aggregate Tables | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3786 | Table Support in XML - Export Support for Aggregate Tables | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.1 | 0 | 0.1 | 0.1
3784 | Summary Screen - Task Summary | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
2887 | Index rebuild is not building partition indexes correctly | Richard Hodges | TBD | 2 - Should | 1.2.2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5
3783 | Summary Screen - Preview Rendering | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.1
3780 | Date Selection Screen - new version | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1.5 | 1.5 | 0 | 1.5 | 0.1
2788 | Wizards are orientated to power users and should/could be simplified | Richard Hodges | TBD | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0
3778 | Date Selection Screen - old version | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.1 | 0 | 0.1 | 0.1
3428 | Service Package is essential to AUM product route but change not picked up | Richard Hodges | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3441 | Errors in loading of employee data | Richard Hodges | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3793 | Wizard Selector - New wizard | Richard Hodges | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 1
2279 | There is no quick way of copying people from one strategy to another , instead t | Roy Wetherall | TBD | 3 - Could | 1.2.2 | In Development | 5 | 0 | 0 | 5 | 5
3566 | Plugin: Search context UI | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
1900 | New Strategies and Products added are not sorted in the tree | Roy Wetherall | Q3 | 3 - Could | 2 | In Development | 1 | 0 | 0 | 1 | 1
1551 | Short cut - product inconsistent | Roy Wetherall | Q3 | 3 - Could | 2 | In Development | 0.5 | 0 | 0 | 0.5 | 0.5
3642 | If you put a value in (e.g for size), you must enter a currency | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3585 | Plugin: Info map, "Delete answer from document" action | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0 | 0.5 | 0 | #N/A
3586 | Plugin: Info map, "Mark as candidate" action | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0 | 0.5 | 0 | #N/A
3587 | Plugin: Information panel | Roy Wetherall | V2C3 | 3 - Could | 2 | In Development | 1.5 | 1.3 | 0 | 1.3 | 1.3
3588 | Plugin: Opp details information panel | Roy Wetherall | V2C3 | 3 - Could | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3589 | Plugin: Opp details status panel | Roy Wetherall | V2C3 | 3 - Could | 2 | In Development | 1 | 1 | 0 | 1 | 1
3591 | Plugin: Apply Word macro's to formating of tables upon insert from wizard | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | 0.5
3592 | Plugin: Info map infomation panel | Roy Wetherall | V2C3 | 3 - Could | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3612 | Changing consultant in edit screen causes server error on import | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3615 | timed out on the Opportunities grid gives error | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3616 | when you are in the opportunities grid 'Copy to Clipboard' copies wrong info | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3620 | New Opp, Fund Information, 'Specify existing fund' - existing funds not shown | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3624 | No confirmation when Cancelling the creation of a new Opp | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3561 | Plugin: "Print" action | Roy Wetherall | V2C3 | 3 - Could | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3641 | Currency: should be able to specify units (millions, etc) | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3582 | Plugin: Info map, "Revert to published answer" action | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | #N/A
3643 | Add a 'view details' option when adding people | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3644 | Date Validation: Internal Deadline >= Date Received. | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3649 | scheme type only enabled if fund type is pension | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3653 | If you click on the checkbox next to a vehicle it should highlight it.... | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3828 | Edit product may retreive incorrect version on edit | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3829 | Constraint tasks, available inappropriately => errors with deleted constraint | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3674 | Vehicle allocation Grid columns have no titles | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3746 | Plugin : Save as Standard | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 3 | 3 | 0 | 3 | 3
3750 | Delete product in published or staging area causes class cast exception | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3811 | Clone product and clone vehicle give class cast exception | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3836 | New Opp Wizard - Step 7 page is too large for dialog | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3845 | PIM Tree node should be removed from the Staging 'Preview Work Area' | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3639 | Typo - specify spelt wrong | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3550 | Plugin: Human readable tags | Roy Wetherall | V2C3 | 2 - Should | 2 | In Development | 1 | 1 | 0 | 1 | 0.01
3160 | Datalists in the CDB area (Companies and QSets below that) forget column widths | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3189 | Strategy Roles mapper does not maintain date order of the roles in data | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3210 | Edit person - questionable selection of office for individual from history | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3232 | Strategy can have a start date after the end date | Roy Wetherall | Q3 | 3 - Could | 2 | In Development | 0 | 0 | 0 | 0 | 0
3416 | Shortcut use after deletion of product by other client gives error as pt 2957 | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3402 | Opportunity Field , shoud display opportunity name as the label | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3407 | Searching by Selecting text from Within question and right click | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3408 | Need Control of Graphics on Paste into Document | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3418 | Add product in a workarea locks product creation in published | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3420 | Change Staging Area - NewProduct's Manufacturing company- Nullpointer error | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3422 | Failure of Product edit without error | Roy Wetherall | Q3 | 2 - Should | 2 | In Development | 0 | 0 | 0 | 0 | 0
3700 | Plugin doesn't start but causes an error starting Word- Infragistics reference | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3584 | Plugin: Info map, global tasks | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | #N/A
3720 | Link Products to Strategy dialog typo - misses word select in dialog description | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0
3583 | Plugin: Info map, preview latest action | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | #N/A
3555 | Plugin: Content I'm Editing Grid | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3559 | Plugin: "Save as external copy" task | Roy Wetherall | V2C3 | 2 - Should | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3560 | Plugin: "Save As" task | Roy Wetherall | V2C3 | 3 - Could | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3562 | Plugin: Update exisiting tag manager implementation | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 1 | 0 | 1.5 | 0 | #N/A
3567 | Plugin: Search options UI | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3570 | Plugin: Search "Answer Preview" action | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0 | 0.5 | 0 | #N/A
3571 | Plugin: Search "View realted items" action | Roy Wetherall | V2C3 | 2 - Should | 2 | In Development | 1.5 | 1.5 | 0 | 1.5 | 1.5
3573 | Plugin: Canned search queries | Roy Wetherall | V2C3 | 2 - Should | 2 | In Development | 1 | 1 | 0 | 1 | 1
3574 | Plugin: Insert answer action | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0 | 1.5 | 0 | 0.1
3579 | Plugin: Info map grid containing answers in the document | Roy Wetherall | Q2 | 1 - Must | 2 | In Development | 1 | 0 | 1 | 0 | 0
3580 | Plugin: Info map, "Diff with published" action | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 1 | 1 | 0 | 1 | #N/A
3581 | Plugin: Info map, "Refresh answer" action | Roy Wetherall | V2C3 | 1 - Must | 2 | In Development | 0.5 | 0.5 | 0 | 0.5 | 0.5
3247 | Word Plugin: Shared login | Roy Wetherall | V2C3 | 3 - Could | 2 | In Development | 3 | 3 | 0 | 3 | 3
3718 | Link Person to product (or strategy) gives MQL error | Roy Wetherall | Q3 | 1 - Must | 2 | In Development | 0 | 0 | 0 | 0 | 0

## V2.1Inception
Requirement | Priority | LB Elab | Dev Elab | LB Const | Dev Const | Status
Answer/Issue Management | 1 | 3 | 10 | 3 | 18 | PHH: Test Word macro based approach against our plugin. PHH : Review use cases produced by TJB
AUM Import Enhancements | 1 | 2 | 4 | 2 | 15 | PHH to lead. Focus on acc/client/fund and identify maximum value for minimum effort.
Embedded Data Changes and Content | 1 | 2 | 5 | 2 | 18 | TJB: To produce use cases.
Overspill on RFP | 1 | 3 | 4 | 4 | 10
Desktop Client UI Improvements (new homepage, portal, views…) | 1 | 4 | 8 | 4 | 18 | TJB : Review V2 against demo
Product History / Auditing | 1 | 2 | 5 | 3 | 10 | TJB : Investigate precise requirement
Continued bug fixing of V2.0 | 1 |  |  |  | 15
Product Information Management Enhancements | 1.5
Information Collection Surveys | 2
Content Maintenance Schedule | 2
Review and Approval Controls | 2
Email based alerts | 2
Zero-Footprint Client | 2
Data Model Extensions | 2
Extend Public API Interface | 2
Validation Enhancements (driven by import enhancements) | 2
Improve syntax of MQL | 2 |  |  |  |  | DC lead.
User Feedback on v2.0 | 3
Soft Model Configuration & Maintenance | 3
Information Distribution Pipeline | 3
Investment Product Communications Dashboard | 3
Data Distribution | 3
Core Capability for Web Distribution | 3
Factsheet Production | 3
Automated Updates to Investment Consultants | 3
‘On-Demand’ Integration Interface | 3 |  |  |  |  | JN says this is more important than a "3" but could be a demo
Enhancements from PT | TBD |  |  |  |  | TJB : Review PT enhancements

## V2.1Analysis
Priority
Data | 1 | 1.5 | 2 | 3 | TBD | (blank) | Grand Total | Available | Diff(Prio1)
Sum of LB Elab | 16 | [5 empty] | 16 | 16 | 0
Sum of Dev Elab | 36 | [5 empty] | 36 | 36 | 0
Sum of LB Const | 18 | [5 empty] | 18 | 18 | 0
Sum of Dev Const | 104 | [5 empty] | 104 | 104 | 0

## Risks
| Risk | Mitigation | Status
1 | Initial indications are that WebSphere performance maybe significant lower than JBoss for our application. | DC is investigating to determine the scope of the problem and whether we can change aspects of our application to better suit WebSphere | Ongoing
2 | V2.0 functionality may not meet the expectations of non-development groups within Activiti. | Summary of V2.0 functionality produced and distributed. | Done
|  | Produce early experience versions. | Ongoing
3 | QA resources are limited and transition phase is only 4 weeks. Risk that quality maybe compromised. | Implement automated continuous integration and test. | Done
|  | Investigate automated UI test tools | Ongoing
|  | Update Business Acceptance Tests to structure testing by non-QA staff. Encourage cross-business involvement in testing. | Ongoing
|  | Produce early experience versions | Ongoing
|  | Improve check-in review process. | Done
|  | Kick-start transition phase with presentation of software highlighting new functionality. | Ongoing
4 | Consultancy maybe distracted from full involvement in transition phase for V2.0 | Obtain early commitment and produce plan for transition phase with consultancy | Ongoing
|  | Kick-start transition phase with presentation of software highlighting new functionality. | Ongoing
5 | Developers laptops prone to failure | Purchase external drive for imaging drives reducing rebuild time. Encourage developers to perform regular images. | Ongoing
6 | Developers laptops insufficiently powerful to run development system (particularly with WebSphere) | Developers continue to use JBoss until WebSphere development environment is proven. | Ongoing
|  | ND investigating options to improve performance of development environment. | Ongoing
7 | Product demo may not correctly reflect actual product or product plans | Produce gap analysis between demo and product / product plan. | Ongoing
8 | Engineering maybe asked to support different databases, hardware or application servers at short notice. | Ensure consultancy and pre-sales are aware of the non-trivial nature of porting to new databases and platforms. | Ongoing
|  | Produce estimates for possible porting activities. | Ongoing
9 | IBM teaming agreement creates unexpected work | Review and discuss IBM teaming agreement. | Ongoing
10 | There may be gaps between developers task list and original use cases for V2.0 development. | Conduct detailed review of use cases against task lists | Done - 1 week slippage
11 | Existing two AIX boxes may prove insufficient to develop and test AIX version. | Investigate AIX hardware options and lead time. Be prepared to order new hardware at short notice. | Ongoing
12 | Demonstrations, Pilots, POCs create unplanned work for development. | Some contingency included in plan but otherwise replanning will be needed if circumstances change. | Ongoing
13 | Decisions on content to be included in V2.1 may not be supported by non-development groups. | Ensure stage gates between engineering phases involve all interested parties within Activiti. | Ongoing
14 | Migration process at Fidelity undecided (including extent of data to be migrated). This could create additional development work. | Review migration process with consultancy. | Ongoing